## Road Map
Hany Helper - Road Map
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/02/20 | Iteration 2 - 10/30/20 | Iteration 3 - 11/06/20 | Iteration 4 - 12/04/20
Module 1 - Build Profile | 1.01 Identify as a Helper or Customer | [5 empty] | features implemented last semester
1.02 Label profile from an array of skills or trades
1.03 Describe experience and expertise
| 1.04 Add professional photos | 2 | x
| 1.05 Identify location | 2 | x
| 1.07 Set availability times | 1 | x
Module 2 - User's Account | 2.01 Reset password | 2 | x
| 2.02 Manage email preferences | 2 | x
| 2.03 Deactivate an account | 3 | x
2.07 Register for an Account
2.08 Sign into an Account
Module 3 - Searching | 3.01 View Helpers by trade | 3 |  | x
| 3.02 Filter Helpers by location, fee or experience | 4 |  |  | x
| 3.03 Sort by rating, fee or availability | 3 |  | x
| 3.05 Filter Customer jobs by location, trade or free | 3 |  | x
Module 4 - Listing | 4.01 List a job that details services required | 3 |  | x
| 4.02 Categorize post by trade | 3 |  |  |  | x
| 4.03 Set an initial fee | 2 |  |  |  | x
| 4.05 Cancel a job | 2 |  |  |  | x
Module 6 - Booking | 6.01 Assign a user to an existing job listing | 3 |  |  | x
| 6.02 Set a price, either hourly or by project completion | 1 |  |  | x
| 6.03 View all current bookings | 4 |  |  | x
| 6.05 Cancel a booking | 3 |  |  |  | x
|  | Velocity | 12 | 12 | 12 | 10

## Story Map
Epics |  | Handy Helper - User Story Map
Epic 1 - Build Profile |  | Epic 1 - Build Profile | Epic 2 - User's Account | Epic 3 - Searching | Epic 4 - Listing | Epic 6 - Booking | Iteration 1
Epic 2 - User's Account | User Stories | 1.04 Add professional photos 1.05 Identify location 1.07 Set availability times | 2.01 Reset password 2.02 Manage email preferences 2.03 Deactivate an account
Epic 3 -Searching
Epic 4 - Listing
Epic 6 - Booking |  |  |  | 3.01 View Helpers by trade 3.03 Sort by rating, fee or availability 3.05 Filter Customer jobs by location, trade or free | 4.01 List a job that details services required |  | Iteration 2
|  |  |  | 3.02 Filter Helpers by location, fee or experience |  | 6.01 Assign a user to an existing job listing 6.02 Set a price, either hourly or by project completion 6.03 View all current bookings | Iteration 3
[5 empty] | 4.02 Categorize post by trade 4.03 Set an initial fee 4.05 Cancel a job | 6.05 Cancel a booking | Iteration 4