## R1 I1
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Create Reset Password Button | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
2 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Implement reset password functionality | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
3 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Implement GUI requirements | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
4 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Implement Crosscut FV - Field Validation | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
5 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Implement validation on fields to ensure accurate modifications: New Passwords is required and not null/blank | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
6 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Implement validation on fields to ensure accurate modifications: Password needs to meet validation criteria | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
7 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Implement validation on fields to ensure accurate modifications: Verify Password when password is updated. | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
8 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Implement validation on fields to ensure accurate modifications: Verify passwords are the same in both text fields | 2020-09-17 | 2020-09-24 | 100%
9 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Create test cases for Functionality | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
10 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Create test cases for GUI Functionality | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
11 | R1 - I1 | 02. User's Account | 2.01 | Reset password | Execute test cases and document the test execution log | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger
12 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Implement Manage email preferences functionality | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
13 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Implement GUI requirements | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
14 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Implement Email Input Field | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
15 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Implement validation on fields to ensure accurate modifications: Email Address is required and not null/blank | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
16 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Implement validation on fields to ensure accurate modifications: Email Address is different from previous one | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
17 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Implement validation on fields to ensure accurate modifications: Email needs to meet validation criteria | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
18 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Implement validation on fields to ensure accurate modifications: Verify Email when Email is updated. | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
19 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Implement Crosscut FV - Field Validation | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
20 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Develop Test Cases for Manage Email Functionality | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
21 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Develop test cases for GuI Functionality | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
22 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Develop Test Cases for Field Validation | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
23 | R1 - I1 | 02. User's Account | 2.02 | Manage email preferences | Execute test cases and document the test execution log | 2020-09-17 | 2020-09-24 | 100% | Yixuan Ma
24 | R1 - I1 | 02. User's Account | 2.03 | Deactivate an account | Implement deactivate an account functionality | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger / Yixuan Ma
25 | R1 - I1 | 02. User's Account | 2.03 | Deactivate an account | Create Active Account Checkbox | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger / Yixuan Ma
26 | R1 - I1 | 02. User's Account | 2.03 | Deactivate an account | Create a Save Button | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger / Yixuan Ma
27 | R1 - I1 | 02. User's Account | 2.03 | Deactivate an account | Confirm User Receives Email confirmation after deactivation | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger / Yixuan Ma
28 | R1 - I1 | 02. User's Account | 2.03 | Deactivate an account | Create Test Cases for Deactivate an account functionality | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger / Yixuan Ma
29 | R1 - I1 | 02. User's Account | 2.03 | Deactivate an account | Create test cases for GUI Functionality | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger / Yixuan Ma
30 | R1 - I1 | 02. User's Account | 2.03 | Deactivate an account | Execute test cases and document the test execution log | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger / Yixuan Ma
31 | R1 - I1 | 01. Build Profile | 1.05 | Identify location | Implement Identify Location Functionality | 2020-09-17 | 2020-09-24 | 100% | Marlene Hasslinger / Yixuan Ma
32 | R1 - I1 | 01. Build Profile | 1.05 | Identify location | Create Location Text Field in Account Settings | 2020-09-17 | 2020-09-24 | 100% | Veenus Thakkar
33 | R1 - I1 | 01. Build Profile | 1.05 | Identify location | Create a Save Button | 2020-09-17 | 2020-09-24 | 100% | Veenus Thakkar
34 | R1 - I1 | 01. Build Profile | 1.05 | Identify location | Implement Crosscut FV - Field Validation | 2020-09-17 | 2020-09-24 | 100% | Veenus Thakkar
35 | R1 - I1 | 01. Build Profile | 1.05 | Identify location | Implement GUI requirements | 2020-09-17 | 2020-09-24 | 100% | Veenus Thakkar
36 | R1 - I1 | 01. Build Profile | 1.05 | Identify location | Implement validation on fields to ensure accurate modifications: Location is required and not null/blank | 2020-09-17 | 2020-09-24 | 100% | Veenus Thakkar
37 | R1 - I1 | 01. Build Profile | 1.05 | Identify location | Develop Test Cases for Identify Location Core Functionality | 2020-09-17 | 2020-09-24 | 100% | Veenus Thakkar
38 | R1 - I1 | 01. Build Profile | 1.05 | Identify location | Develop Test cases for GUI Functionality | 2020-09-17 | 2020-09-24 | 100% | Veenus Thakkar
39 | R1 - I1 | 01. Build Profile | 1.05 | Identify location | Execute test cases and document the test execution log | 2020-09-17 | 2020-09-24 | 100% | Veenus Thakkar
40 | R1 - I1 | 01. Build Profile | 1.04 | Add professional photos | Create Add Photos Button | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan
41 | R1 - I1 | 01. Build Profile | 1.04 | Add professional photos | Implement Add Photos functionality | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan
42 | R1 - I1 | 01. Build Profile | 1.04 | Add professional photos | Implement GUI requirements | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan
43 | R1 - I1 | 01. Build Profile | 1.04 | Add professional photos | View Added Photos | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan
44 | R1 - I1 | 01. Build Profile | 1.04 | Add professional photos | Implement Crosscut Exception Handling | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan
45 | R1 - I1 | 01. Build Profile | 1.04 | Add professional photos | Create Test Cases for Add professional photos functionality | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan
46 | R1 - I1 | 01. Build Profile | 1.04 | Add professional photos | Create Test Cases for Exception Handling | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan
47 | R1 - I1 | 01. Build Profile | 1.04 | Add professional photos | Create test cases for GUI Functionality | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan
48 | R1 - I1 | 01. Build Profile | 1.04 | Add professional photos | Execute test cases and document the test execution log | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan
49 | R1 - I1 | 01. Build Profile | 1.07 | Set availability times | Create Availability Text Box in Account Settings | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan / Veenus Thakkar
50 | R1 - I1 | 01. Build Profile | 1.07 | Set availability times | Implement set availability times functionality | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan /Veenus Thakkar
51 | R1 - I1 | 01. Build Profile | 1.07 | Set availability times | Implement GUI requirements | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan /Veenus Thakkar
52 | R1 - I1 | 01. Build Profile | 1.07 | Set availability times | Implement Crosscut Internal Entitlements | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan / Veenus Thakkar
53 | R1 - I1 | 01. Build Profile | 1.07 | Set availability times | Create Submit Button | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan / Veenus Thakkar
54 | R1 - I1 | 01. Build Profile | 1.07 | Set availability times | Develop Test Cases for set availability times functionality | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan / Veenus Thakkar
55 | R1 - I1 | 01. Build Profile | 1.07 | Set availability times | Develop Test Cases for Internal Entitlements | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan / Veenus Thakkar
56 | R1 - I1 | 01. Build Profile | 1.07 | Set availability times | Develop Test Cases for GUI Functionality | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan / Veenus Thakkar
57 | R1 - I1 | 01. Build Profile | 1.07 | Set availability times | Execute test cases and document the test execution log | 2020-09-25 | 2020-10-02 | 100% | Curt Morgan / Veenus Thakkar

## R1 I2
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I2 | 03. Searching | 3.01 | View Helpers by trade | Implement View Helpers by trade functionality | 2020-10-09 | 2020-10-16 | 100% | Curt Morgan
2 | R1 - I2 | 03. Searching | 3.01 | View Helpers by trade | Implement GUI requirements | 2020-10-09 | 2020-10-16 | 100% | Curt Morgan
3 | R1 - I2 | 03. Searching | 3.01 | View Helpers by trade | Implement search by skill Input Field | 2020-10-09 | 2020-10-16 | 100% | Curt Morgan
4 | R1 - I2 | 03. Searching | 3.01 | View Helpers by trade | Implement Crosscut FV - Field Validation | 2020-10-09 | 2020-10-16 | 100% | Veenus Thakkar/ Marlene Hasslinger
5 | R1 - I2 | 03. Searching | 3.01 | View Helpers by trade | Create Test Cases for view helpers by trade functionality | 2020-10-09 | 2020-10-16 | 100% | Veenus Thakkar/ Marlene Hasslinger
6 | R1 - I2 | 03. Searching | 3.01 | View Helpers by trade | Create test cases for GUI Functionality | 2020-10-09 | 2020-10-16 | 100% | Veenus Thakkar/ Marlene Hasslinger
7 | R1 - I2 | 03. Searching | 3.01 | View Helpers by trade | Create test cases for field validation | 2020-10-09 | 2020-10-16 | 100% | Veenus Thakkar/ Marlene Hasslinger
8 | R1 - I2 | 03. Searching | 3.01 | View Helpers by trade | Execute test cases and document the test execution log | 2020-10-09 | 2020-10-16 | 50% | Veenus Thakkar/ Marlene Hasslinger
9 | R1 - I2 | 03. Searching | 3.03 | Filter by fee or availability | Implement Filter by fee or availability functionality | 2020-10-09 | 2020-10-16 | 100% | Curt Morgan
10 | R1 - I2 | 03. Searching | 3.03 | Filter by fee or availability | Implement GUI requirements | 2020-10-09 | 2020-10-16 | 100% | Curt Morgan
11 | R1 - I2 | 03. Searching | 3.03 | Filter by fee or availability | Implement the Input Field | 2020-10-09 | 2020-10-16 | 100% | Curt Morgan
12 | R1 - I2 | 03. Searching | 3.03 | Filter by fee or availability | Create Test Cases for Filter by fee or availability functionality | 2020-10-09 | 2020-10-16 | 100% | Veenus Thakkar/ Marlene Hasslinger
13 | R1 - I2 | 03. Searching | 3.03 | Filter by fee or availability | Create test cases for GUI Functionality | 2020-10-09 | 2020-10-16 | 100% | Veenus Thakkar/ Marlene Hasslinger
14 | R1 - I2 | 03. Searching | 3.03 | Filter by fee or availability | Create test cases for field validation | 2020-10-09 | 2020-10-16 | 100% | Veenus Thakkar/ Marlene Hasslinger
15 | R1 - I2 | 03. Searching | 3.03 | Filter by fee or availability | Execute test cases and document the test execution log | 2020-10-09 | 2020-10-16 | 100% | Veenus Thakkar/ Marlene Hasslinger
16 | R1 - I2 | 03. Searching | 3.05 | Filter Customer jobs by location, trade or free | Implement Filter Customer jobs by location, trade or free functionality | 2020-10-16 | 2020-10-23 | 100% | Curt Morgan
17 | R1 - I2 | 03. Searching | 3.05 | Filter Customer jobs by location, trade or free | Implement GUI requirements | 2020-10-16 | 2020-10-23 | 100% | Curt Morgan
18 | R1 - I2 | 03. Searching | 3.05 | Filter Customer jobs by location, trade or free | Implement the Input Field | 2020-10-16 | 2020-10-23 | 100% | Curt Morgan
19 | R1 - I2 | 03. Searching | 3.05 | Filter Customer jobs by location, trade or free | Create Test Cases for Filter by fee or availability functionality | 2020-10-16 | 2020-10-23 | 100% | Veenus Thakkar/ Marlene Hasslinger
20 | R1 - I2 | 03. Searching | 3.05 | Filter Customer jobs by location, trade or free | Create test cases for GUI Functionality | 2020-10-16 | 2020-10-23 | 100% | Veenus Thakkar/ Marlene Hasslinger
21 | R1 - I2 | 03. Searching | 3.05 | Filter Customer jobs by location, trade or free | Create test cases for field validation | 2020-10-16 | 2020-10-23 | 100% | Veenus Thakkar/ Marlene Hasslinger
22 | R1 - I2 | 03. Searching | 3.05 | Filter Customer jobs by location, trade or free | Execute test cases and document the test execution log | 2020-10-16 | 2020-10-23 | 50% | Veenus Thakkar/ Marlene Hasslinger
23 | R1 - I2 | 04. Listing a job | 4.01 | List a job that details services required | Implement List a job that details services required functionality | 2020-10-16 | 2020-10-23 | 100% | Curt Morgan
24 | R1 - I2 | 04. Listing a job | 4.01 | List a job that details services required | Implement GUI requirements | 2020-10-16 | 2020-10-23 | 100% | Curt Morgan
25 | R1 - I2 | 04. Listing a job | 4.01 | List a job that details services required | Implement the Input Field | 2020-10-16 | 2020-10-23 | 100% | Curt Morgan
26 | R1 - I2 | 04. Listing a job | 4.01 | List a job that details services required | Create Test Cases for Filter by fee or availability functionality | 2020-10-16 | 2020-10-23 | 100% | Veenus Thakkar/ Marlene Hasslinger
27 | R1 - I2 | 04. Listing a job | 4.01 | List a job that details services required | Create test cases for GUI Functionality | 2020-10-16 | 2020-10-23 | 100% | Veenus Thakkar/ Marlene Hasslinger
28 | R1 - I2 | 04. Listing a job | 4.01 | List a job that details services required | Create test cases for field validation | 2020-10-16 | 2020-10-23 | 100% | Veenus Thakkar/ Marlene Hasslinger
29 | R1 - I2 | 04. Listing a job | 4.01 | List a job that details services required | Execute test cases and document the test execution log | 2020-10-16 | 2020-10-23 | 100% | Veenus Thakkar/ Marlene Hasslinger

## R2 I3
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I3 | 03. Searching | 3.02 | Filter Helpers by Location | Implement View Helpers by trade functionality | 2020-10-23 | 2020-10-30 | 100% | Curt Morgan
2 | R2 - I3 | 03. Searching | 3.02 | Filter Helpers by Location | Implement GUI requirements | 2020-10-23 | 2020-10-30 | 100% | Curt Morgan
3 | R2 - I3 | 03. Searching | 3.02 | Filter Helpers by Location | Implement filter filed | 2020-10-23 | 2020-10-30 | 100% | Curt Morgan
4 | R2 - I3 | 03. Searching | 3.02 | Filter Helpers by Location | Implement Crosscut FV - Field Validation | 2020-10-23 | 2020-10-30 | 100% | Curt Morgan
5 | R2 - I3 | 03. Searching | 3.02 | Filter Helpers by Location | Create test cases for Functionality | 2020-10-23 | 2020-10-30 | 100% | Curt Morgan
6 | R2 - I3 | 03. Searching | 3.02 | Filter Helpers by Location | Create test cases for GUI Functionality | 2020-10-23 | 2020-10-30 | 100% | Curt Morgan
7 | R2 - I3 | 03. Searching | 3.02 | Filter Helpers by Location | Create test cases for Field Validation | 2020-10-23 | 2020-10-30 | 100% | Curt Morgan
8 | R2 - I3 | 03. Searching | 3.02 | Filter Helpers by Location | Execute test cases and document the test execution log | 2020-10-23 | 2020-10-30 | 100% | Curt Morgan
9 | R2 - I3 | 06. Booking | 6.01 | Assign a user to an existing listing | Implement Assign a user to an existing listing functionality | 2020-10-23 | 2020-10-30 | 100% | Marlene Hasslinger
10 | R2 - I3 | 06. Booking | 6.01 | Assign a user to an existing listing | Implement GUI requirements | 2020-10-23 | 2020-10-30 | 100% | Marlene Hasslinger
11 | R2 - I3 | 06. Booking | 6.01 | Assign a user to an existing listing | Implement Crosscut CN - Connectivity | 2020-10-23 | 2020-10-30 | 100% | Marlene Hasslinger
12 | R2 - I3 | 06. Booking | 6.01 | Assign a user to an existing listing | Create test cases for GUI functionality | 2020-10-23 | 2020-10-30 | 100% | Marlene Hasslinger
13 | R2 - I3 | 06. Booking | 6.01 | Assign a user to an existing listing | Create test cases for Core Functionality | 2020-10-23 | 2020-10-30 | 100% | Marlene Hasslinger
14 | R2 - I3 | 06. Booking | 6.01 | Assign a user to an existing listing | Create test cases for Connectivity | 2020-10-23 | 2020-10-30 | 100% | Marlene Hasslinger
15 | R2 - I3 | 06. Booking | 6.01 | Assign a user to an existing listing | Execute test cases and document the test execution log | 2020-10-23 | 2020-10-30 | 100% | Marlene Hasslinger
16 | R2 - I3 | 06. Booking | 6.02 | Set a price by hour or project completion | Implement Set a price by hour or project completion functionality | 2020-10-30 | 2020-11-06 | 100% | Veenus Thakkar
17 | R2 - I3 | 06. Booking | 6.02 | Set a price by hour or project completion | Implement GUI requirements | 2020-10-30 | 2020-11-06 | 100% | Veenus Thakkar
18 | R2 - I3 | 06. Booking | 6.02 | Set a price by hour or project completion | Implement Crosscut FV - Field Validation | 2020-10-30 | 2020-11-06 | 100% | Veenus Thakkar
19 | R2 - I3 | 06. Booking | 6.02 | Set a price by hour or project completion | Implement Input filed | 2020-10-30 | 2020-11-06 | 100% | Veenus Thakkar
20 | R2 - I3 | 06. Booking | 6.02 | Set a price by hour or project completion | Create test cases for GUI functionality | 2020-10-30 | 2020-11-06 | 100% | Veenus Thakkar
21 | R2 - I3 | 06. Booking | 6.02 | Set a price by hour or project completion | Create test cases for Functionality | 2020-10-30 | 2020-11-06 | 100% | Veenus Thakkar
22 | R2 - I3 | 06. Booking | 6.02 | Set a price by hour or project completion | Create test cases for field validation | 2020-10-30 | 2020-11-06 | 100% | Veenus Thakkar
23 | R2 - I3 | 06. Booking | 6.02 | Set a price by hour or project completion | Execute test cases and document the test execution log | 2020-10-30 | 2020-11-06 | 100% | Veenus Thakkar
24 | R2 - I3 | 06. Booking | 6.03 | View all current bookings | Create View all current bookings functionality | 2020-10-30 | 2020-11-06 | 100% | Abhinav Bhatt
25 | R2 - I3 | 06. Booking | 6.03 | View all current bookings | Implement GUI requirements | 2020-10-30 | 2020-11-06 | 100% | Abhinav Bhatt
26 | R2 - I3 | 06. Booking | 6.03 | View all current bookings | Implement Crosscut CN - Connectivity | 2020-10-30 | 2020-11-06 | 100% | Abhinav Bhatt
27 | R2 - I3 | 06. Booking | 6.03 | View all current bookings | Implement Crosscut PF - Performance | 2020-10-30 | 2020-11-06 | 100% | Abhinav Bhatt
28 | R2 - I3 | 06. Booking | 6.03 | View all current bookings | Create test cases for Functionality | 2020-10-30 | 2020-11-06 | 100% | Abhinav Bhatt
29 | R2 - I3 | 06. Booking | 6.03 | View all current bookings | Create test cases for GUI functionality | 2020-10-30 | 2020-11-06 | 100% | Abhinav Bhatt
30 | R2 - I3 | 06. Booking | 6.03 | View all current bookings | Create test cases for connectivity | 2020-10-30 | 2020-11-06 | 100% | Abhinav Bhatt
31 | R2 - I3 | 06. Booking | 6.03 | View all current bookings | Create test cases for performance | 2020-10-30 | 2020-11-06 | 100% | Abhinav Bhatt
32 | R2 - I3 | 06. Booking | 6.03 | View all current bookings | Execute test cases and document the test execution log | 2020-10-30 | 2020-11-06 | 100% | Abhinav Bhatt

## R2 I4
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I4 | 04. List a job | 4.02 | Categorize posts by trade | Implement Categorize posts by trade functionality | 2020-11-06 | 2020-11-13 | 100% | Marlene Hasslinger
2 | R2 - I4 | 04. List a job | 4.02 | Categorize posts by trade | Implement GUI requirements | 2020-11-06 | 2020-11-13 | 100% | Marlene Hasslinger
3 | R2 - I4 | 04. List a job | 4.02 | Categorize posts by trade | Implement Crosscut FV - Field Validation | 2020-11-06 | 2020-11-13 | 100% | Marlene Hasslinger
4 | R2 - I4 | 04. List a job | 4.02 | Categorize posts by trade | Develop test cases for core functionality | 2020-11-06 | 2020-11-13 | 100% | Marlene Hasslinger
5 | R2 - I4 | 04. List a job | 4.02 | Categorize posts by trade | Develop test cases for GUI functionality | 2020-11-06 | 2020-11-13 | 100% | Marlene Hasslinger
6 | R2 - I4 | 04. List a job | 4.02 | Categorize posts by trade | Develop test cases for field validation | 2020-11-06 | 2020-11-13 | 100% | Marlene Hasslinger
7 | R2 - I4 | 04. List a job | 4.02 | Categorize posts by trade | Execute test cases and document the test execution log | 2020-11-06 | 2020-11-13 | 100% | Marlene Hasslinger
8 | R2 - I4 | 04. List a job | 4.03 | Set an initial fee | Implement Set an initial fee functionality | 2020-11-13 | 2020-11-20 | 100% | Veenus Thakkar
9 | R2 - I4 | 04. List a job | 4.03 | Set an initial fee | Implement GUI requirements | 2020-11-13 | 2020-11-20 | 100% | Veenus Thakkar
10 | R2 - I4 | 04. List a job | 4.03 | Set an initial fee | Implement Crosscut FV - Field Validation | 2020-11-13 | 2020-11-20 | 100% | Veenus Thakkar
11 | R2 - I4 | 04. List a job | 4.03 | Set an initial fee | Implement Input fields | 2020-11-13 | 2020-11-20 | 100% | Veenus Thakkar
12 | R2 - I4 | 04. List a job | 4.03 | Set an initial fee | Develop test cases for GUI functionality | 2020-11-13 | 2020-11-20 | 100% | Veenus Thakkar
13 | R2 - I4 | 04. List a job | 4.03 | Set an initial fee | Develop test cases for Core Functionality | 2020-11-13 | 2020-11-20 | 100% | Veenus Thakkar
14 | R2 - I4 | 04. List a job | 4.03 | Set an initial fee | Develop test cases for field validation | 2020-11-13 | 2020-11-20 | 100% | Veenus Thakkar
15 | R2 - I4 | 04. List a job | 4.03 | Set an initial fee | Execute test cases and document the test execution log | 2020-11-13 | 2020-11-20 | 100% | Veenus Thakkar
16 | R2 - I4 | 04. List a job | 4.05 | Cancel a job | Implement Cancel a job functionality | 2020-11-20 | 2020-11-27 | 100% | Curt Morgan
17 | R2 - I4 | 04. List a job | 4.05 | Cancel a job | Implement GUI requirements | 2020-11-20 | 2020-11-27 | 100% | Curt Morgan
18 | R2 - I4 | 04. List a job | 4.05 | Cancel a job | Implement Crosscut CN - Connectivity | 2020-11-20 | 2020-11-27 | 100% | Curt Morgan
19 | R2 - I4 | 04. List a job | 4.05 | Cancel a job | Implement Crosscut Enrichment | 2020-11-20 | 2020-11-27 | 100% | Curt Morgan
20 | R2 - I4 | 04. List a job | 4.05 | Cancel a job | Develop test cases for Core Functionality | 2020-11-20 | 2020-11-27 | 100% | Curt Morgan
21 | R2 - I4 | 04. List a job | 4.05 | Cancel a job | Develop test cases for GUI functionality | 2020-11-20 | 2020-11-27 | 100% | Curt Morgan
22 | R2 - I4 | 04. List a job | 4.05 | Cancel a job | Develop Test cases for Enrichment | 2020-11-20 | 2020-11-27 | 100% | Curt Morgan
23 | R2 - I4 | 04. List a job | 4.05 | Cancel a job | Develop Test cases for Connectivity | 2020-11-20 | 2020-11-27 | 100% | Curt Morgan
24 | R2 - I4 | 04. List a job | 4.05 | Cancel a job | Execute test cases and document the test execution log | 2020-11-20 | 2020-11-27 | 100% | Curt Morgan
25 | R2 - I4 | 06. Booking | 6.05 | Cancel a booking | Implement Cancel a booking functionality | 2020-11-27 | 2020-12-04 | 100% | Curt Morgan
26 | R2 - I4 | 06. Booking | 6.05 | Cancel a booking | Implement GUI requirements | 2020-11-27 | 2020-12-04 | 100% | Curt Morgan
27 | R2 - I4 | 06. Booking | 6.05 | Cancel a booking | Implement Crosscut CN - Connectivity | 2020-11-27 | 2020-12-04 | 100% | Curt Morgan
28 | R2 - I4 | 06. Booking | 6.05 | Cancel a booking | Implement Crosscut Enrichment | 2020-11-27 | 2020-12-04 | 100% | Curt Morgan
29 | R2 - I4 | 06. Booking | 6.05 | Cancel a booking | Develop test cases for Core Functionality | 2020-11-27 | 2020-12-04 | 100% | Curt Morgan
30 | R2 - I4 | 06. Booking | 6.05 | Cancel a booking | Develop test cases for GUI functionality | 2020-11-27 | 2020-12-04 | 100% | Curt Morgan
31 | R2 - I4 | 06. Booking | 6.05 | Cancel a booking | Develop Test cases for Enrichment | 2020-11-27 | 2020-12-04 | 100% | Curt Morgan
32 | R2 - I4 | 06. Booking | 6.05 | Cancel a booking | Develop Test cases for Connectivity | 2020-11-27 | 2020-12-04 | 100% | Curt Morgan
33 | R2 - I4 | 06. Booking | 6.05 | Cancel a booking | Execute test cases and document the test execution log | 2020-11-27 | 2020-12-04 | 100% | Curt Morgan
34
35
36
37