## Sheet1
Color Coding |  |  | Completed |  |  |  | Spring 2020
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2020-01-28 | 2020-02-04 | 2020-02-11 | 2020-02-18 | 2020-02-25 | 2020-03-03 | 2020-03-10 | 2020-03-17 | 2020-03-24 | 2020-03-31 | 2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-04-28 | 2020-05-05
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2020-01-28 | 2020-02-04 | 100%
| Confirm Project Team Roles |  | ALL | 2020-01-28 | 2020-02-04 | 100%
| Develop two business cases |  | Jack Brody | 2020-01-28 | 2020-02-04 | 100%
| Develop Project Initiation Document (PID) |  | Jack Brody/Yang Zhao | 2020-02-04 | 2020-02-11 | 100%
| Produce initial Project Plan, RACI |  | Jack Brody | 2020-02-11 | 2020-02-18 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Abhinav Bhatt | 2020-02-18 | 2020-02-25 | 100%
| Produce Context Diagram, Define System Interfaces |  | Curtis Morgan | 2020-02-18 | 2020-02-25 | 100%
| Define Business/User Requirements |  | Jack Brody/Abhinav Bhatt | 2020-02-25 | 2020-03-03 | 100%
| Agree to System Requirements types |  | All | 2020-02-25 | 2020-03-03 | 100%
| Produce Fishbone Diagram |  | Marlene Hasslinger | 2020-02-25 | 2020-03-03 | 100%
| Define Functional Decomposition |  | All | 2020-02-25 | 2020-03-03 | 100%
| Produce RCT document |  | All | 2020-02-25 | 2020-03-03 | 100%
| Decide which features to implement this semester |  | All | 2020-03-03 | 2020-03-10 | 100%
| Produce analysis diagrams (Use Case Diagram) |  | Yixuan Ma | 2020-03-10 | 2020-03-17 | 100%
| Produce analysis diagrams (Activity Diagram) |  | Curtis Morgan | 2020-03-10 | 2020-03-17 | 100%
| Produce analysis diagrams (DFD) |  | Abhinav Bhatt/Veenus Atul | 2020-03-10 | 2020-03-17 | 100%
| Define functional requirements (User Stories) |  | Yang Zhao/Marlene Hasslinger | 2020-03-17 | 2020-03-24 | 100%
| Update Project Plan with additional requirements tasks |  | Jack Brody | 2020-03-24 | 2020-03-31 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Database Design (ERD, Data Dictionary-Table specifications) |  | Marlene Hasslinger | 2020-03-17 | 2020-03-24 | 100%
| Architecture design (Logical View) |  | Marlene Hasslinger | 2020-03-24 | 2020-03-31 | 100%
| Architecture design (Process View) |  | Curtis Morgan | 2020-03-24 | 2020-03-31 | 100%
| System Interface Design |  | Curtis Morgan | 2020-03-31 | 2020-04-07 | 100%
| User interface design |  | Curtis Morgan | 2020-03-31 | 2020-04-07 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design |  | Curtis Morgan | 2020-03-31 | 2020-04-07 | 100%
| User Story 1.01 Identifying Profile as Helper or Customer | Build Profile Web Page | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Server route for updating user | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Build Database table for User with a Boolean property isHelper | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
| User Story 1.02 Labeling Profile | Build Profile Web Page | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Server route for updating user | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Design Database table for a User with String column for skills | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Front end data validation | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
| User Story 1.03 Adding Experince/Expertise | Build Profile Web Page | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Server route for updating user | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Build Database table for a User with String column for experience | Curtis Morgan | 2020-04-07 | 2020-04-28
|  | Front end data validation / limit for text field | Curtis Morgan | 2020-04-07 | 2020-04-28 | 70%
| User Story 2.07 Registering an Account/User | Design Sign Up Web Page | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Server route for user creation | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Design Database table for User | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | UX driven design for user feedback on success / error | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Password encryption | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
| User Story 2.08 Signing into Account | Log In Web Page | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | Server route for user login | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
|  | JSON Web Token authentication | Curtis Morgan | 2020-04-07 | 2020-04-28 | 100%
MILESTONE 4: CODING COMPLETED
| Evaluate Features to be Tested |  | Yixuan Ma | 2020-03-31 | 2020-04-07 | 100%
| Plan testing, produce a Test Plan document |  | ALL | 2020-04-07 | 2020-04-14 | 100%
| User Account | Design Test Guidelines and Test Cases 1.01 for Identifying Profile as Helper or Customer | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
|  | Design Test Guidelines and Test Cases s 1.02 for Labeling Profile | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
|  | Design Test Guidelines and Test Cases 1.03 for adding Experince/Expertise | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
|  | Design Test Guidelines and Test Cases 2.07 for Registering an Account/User | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
|  | Design Test Guidelines and Test Cases 2.08 For Signing into Account | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
|  | Execute Test Case 1.01 for Identifying Profile | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
|  | Execute Test Case 1.02 for Labeling Profile | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
|  | Execute Test Case 1.03 for adding Experience/Expertise | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
|  | Execute Test Case 2.07 for Registering an Account/User | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
|  | Execute Test Case 2.08 for Signing into Account | Yixuan Ma / Veenus Thakkar | 2020-04-14 | 2020-04-21 | 100%
| Anaylze Test Results |  | ALL | 2020-04-10 | 2020-04-28 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2020-04-28 | 2020-05-05 | 0%